## Table 1
Corrigendum-2: Pre BID queries response
Party | Sno. | Query | Ask | Response of AEGCL
Garuda UAV | Page - 11 Clause - Technical Evaluation | Minimum Qualifying Marks in Technical - 70 | As stated in the clause minimum qualifying marks in technical is 70, We request you to consider 50 Marks as the minimum Qualifying marks for more participation. | Minimum qualifying marks 60
| Page -35 Clause - 5.6.1 Delivery Schedule Page - 41 Clause - 3.2 | Contract completion period shall be counted from contract commencement date. Completion of the work shall be within 45 days from Contract commencement. The whole works under the scope of this Contract shall be completedwithin 150 (One Hundred Fifty) days from Contract Commencement Date as per completion schedule bar chart (Appendix – 2). | We request you to kindly consider the completion period as 150 Days. | Completion period will be 90 days
| Page -35 Clause - 5.8.0 Terms of Payment | 5.8.2. The terms of payment for the works shall be as follows i. Invoice for 70% of the contract value may be raised by the bidder on delivery of the items as per BoQ other than earthing items and training. In this invoice, 10% advance payment shall be adjusted. The total payment shall be 60% of the contract value after adjusting the advance payment. ii. Remaining 30% payment shall be paid after 100% completion of all the works. iii. Remaining 10% shall be paid as per following a. 2.5% shall be paid after 1st year support. b. 2.5% shall be paid after 2 nd year support. c. Remaining 5% shall be after 3 rd year support. 5.8.3. Documents required along with invoice: Following documents need to be submitted along with invoice – (i) Application for payment (ii) Contractor’s invoice showing LOA reference, Goods description, quantity dispatched, unit reclamation price, total amount (6 Copies) (iii) Physical verification certificate of material received at site by Purchaser/Purchaser’s site representative (For supply). (iv) Work completion certificate (for erection and stringing work | The sum total of the payment term given in RFP is 110% , we request you to kindly consider the below mentioned terms, i. Invoice for 75% of the contract value can be raised on pro rata basis after data acquisition. In this invoice, 15% advance payment shall be adjusted. The total payment shall be 90% of the contract value after adjusting the advance payment. Note: It will be as per the rate bifurcation submitted by successful bidder after award of the contract. ii. Remaining 10% payment shall be paid after 100% completion of all the works. | Payment will be made as per the following provisions- 1)First running bill will be released on completion of minimum 10% of work. 2) Maximum of 4 (Four) nos. of bills will be entertained and each of these bills shall not be less than 10% of the work value. 3) 10% Retention money will be deducted from each bill submitted.
Genesys international Corporation limited |  |  | Requesting for extension of last date of bid submission date for at least two weeks from the current date. | No change.